## PowerQuery
Project Manager | Engagement Name | Track Name | Phase | RAG | Handover due date | Handover completed | Total checks | Total Critical Checks | Completed Critical Checks | Completed | KPI_1 breached | KPI_2 breached | Source.Name
Project Manager1 | 2BP | Governance | Cancelled | Undefined | 2024-06-30 | NULL | 19 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | Service Management | Implement | Red | 2024-11-29 | NULL | 14 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | NETWORK | Implement | Red | 2024-09-17 | NULL | 18 | 0 | 0 | 0.11 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | Governance v2 | Implement | Red | 2024-09-30 | NULL | 8 | 3 | 0 | 0.25 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | Governance | Close | Blue | 2024-06-30 | 04-Apr-2024 | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | Service Management | Close | Blue | 2024-06-30 | 04-Apr-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | OPENSHIFT | Close | Blue | 2024-06-30 | 04-Apr-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | Governance | Cancelled | Undefined | 2024-09-30 | NULL | 19 | 0 | 0 | 0.26 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | SERVICE MANAGEMENT | Cancelled | Undefined | 2024-09-30 | NULL | 14 | 0 | 0 | 0.42 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | Platform | Cancelled | Undefined | 2024-09-30 | NULL | 17 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | Governance | Close | Blue | 2024-12-27 | 03-Oct-2024 | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | OPENSHIFT | Close | Blue | 2024-12-27 | 03-Oct-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | Service Management | Close | Blue | 2024-12-27 | 03-Oct-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | NULL | 19 | 0 | 0 | 0.21 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | NULL | 14 | 0 | 0 | 0.14 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | ANSIBLE | Cancelled | Undefined | 2024-09-30 | NULL | 28 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-06-27 | NULL | 19 | 0 | 0 | 0.31 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-06-27 | NULL | 14 | 0 | 0 | 0.28 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-06-27 | NULL | 17 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | NULL | 19 | 0 | 0 | 0.26 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | NULL | 14 | 0 | 0 | 0.21 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-09-30 | NULL | 17 | 0 | 0 | 0.11 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | VMware | Close | Blue | 2024-04-30 | 27-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Service Management | Implement | Red | 2024-09-30 | NULL | 14 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Network | Close | Blue | 2023-10-31 | 27-May-2024 | 18 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Platform | Close | Blue | 2024-04-30 | 27-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Governance | Cancelled | Undefined | 2024-04-30 | NULL | 19 | 0 | 0 | 0.05 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Backup & Storage | Close | Blue | 2023-10-31 | 27-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | VDI | Close | Blue | 2023-10-31 | 04-Jun-2024 | 46 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Governance - v2 | Delivery | Amber | 2024-09-30 | NULL | 8 | 3 | 3 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Monitoring & Reporting | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | Monitoring & Reporting | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 19 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | Monitoring & Reporting | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 14 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | Governance | Implement | Red | 2024-09-19 | NULL | 19 | 0 | 0 | 0.47 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | VMWare | Implement | Red | 2024-09-19 | NULL | 17 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | Service Management | Implement | Red | 2024-09-19 | NULL | 14 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | NETWORK | Implement | Red | 2024-09-19 | NULL | 18 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | MIDDLEWARE | Implement | Red | 2024-09-19 | NULL | 17 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | IAM Team | Implement | Red | 2024-09-19 | NULL | 17 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | BACKUP & STORAGE TEAM | Implement | Red | 2024-09-19 | NULL | 17 | 0 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | GOVERNANCE | Delivery | Green | 2024-11-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | SERVICE MANAGEMENT | Close | Blue | 2024-08-31 | 16-Sep-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | VMWARE | Close | Blue | 2024-06-30 | 20-Jun-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | BACKUP & STORAGE TEAM | Close | Blue | 2024-05-30 | 30-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | SERVICE MANAGEMENT | Close | Blue | 2024-05-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | GOVERNANCE | Close | Blue | 2024-05-30 | 30-May-2024 | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Cloud | Delivery | Amber | 2024-02-29 | NULL | 17 | 0 | 0 | 1 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Governance | Delivery | Amber | 2024-06-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Service Management | Close | Blue | 2024-06-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | BACKUP & STORAGE TEAM | Close | Blue | 2024-04-30 | 06-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | Governance | Delivery | Amber | 2024-04-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | SERVICE MANAGEMENT | Close | Blue | 2024-04-30 | 10-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | DC-0 | Cloud | Cancelled | Undefined | 2024-03-31 | NULL | 17 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | BACKUP and STORAGE | Cancelled | Undefined | 2024-03-31 | NULL | 17 | 0 | 0 | 0 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | OPENSHIFT | Cancelled | Undefined | 2024-03-31 | NULL | 17 | 0 | 0 | 0.05 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | GOVERNANCE | Cancelled | Undefined | 2024-03-31 | NULL | 19 | 0 | 0 | 0.21 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | Service Management | Cancelled | Undefined | 2024-03-31 | NULL | 14 | 0 | 0 | 0.14 | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | SECURITY | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | SECURITY | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0.06 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | SECURITY | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | SECURITY | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Security | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | Service Management | Cancelled | Undefined | 2024-06-30 | NULL | 12 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | NULL | 16 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | Cloud | Cancelled | Undefined | 2024-06-30 | NULL | 17 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | SECURITY | Cancelled | Undefined | 2024-06-30 | NULL | 4 | 0 | 0 | 0 | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Cloud | Close | Blue | 2024-03-29 | 07-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Governance | Delivery | Amber | 2024-06-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Service Management | Close | Blue | 2024-06-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Cloud | Close | Blue | 2024-03-29 | 07-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Governance | Delivery | Amber | 2024-06-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Service Management | Close | Blue | 2024-06-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Cloud | Close | Blue | 2024-03-29 | 07-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Governance | Delivery | Amber | 2024-06-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Service Management | Close | Blue | 2024-06-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Cloud | Close | Blue | 2024-03-29 | 07-May-2024 | 17 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Governance | Delivery | Amber | 2024-06-30 | NULL | 19 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Service Management | Close | Blue | 2024-06-30 | 30-May-2024 | 14 | 0 | 0 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | GOVERNANCE | Implement | Red | 2024-04-30 | NULL | 8 | 3 | 0 | 0 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | SERVICE MANAGEMENT | Configure | Red | 2024-04-30 | NULL | 12 | 12 | 0 | 0 | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | NETWORK | Configure | Red | 2024-06-30 | NULL | 0 | 0 | 0 | 0 | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Network | Delivery | Amber | 2024-03-31 | NULL | 20 | 6 | 6 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Security | Implement | Red | 2024-07-31 | NULL | 4 | 2 | 1 | 0.75 | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Service Management | Implement | Red | 2024-07-31 | NULL | 12 | 12 | 8 | 0.66 | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Governance | Implement | Red | 2024-07-31 | NULL | 8 | 3 | 3 | 0.75 | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | GOVERNANCE | Close | Blue | 2024-11-30 | 03-Oct-2024 | 8 | 3 | 3 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | SECURITY | Close | Blue | 2024-11-30 | 03-Oct-2024 | 4 | 2 | 2 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | SERVICE MANAGEMENT | Delivery | Amber | 2024-11-30 | NULL | 12 | 12 | 11 | 0.91 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | VMWARE | Close | Blue | 2024-11-30 | 03-Oct-2024 | 19 | 6 | 6 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | GOVERNANCE | Delivery | Green | 2024-11-30 | NULL | 8 | 3 | 3 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | SERVICE MANAGEMENT | Implement | Green | 2024-11-30 | NULL | 12 | 12 | 7 | 0.58 | No | Null | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | SECURITY | Delivery | Green | 2024-11-30 | NULL | 4 | 2 | 2 | 1 | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | VMWARE | Implement | Green | 2024-11-30 | NULL | 19 | 6 | 0 | 0 | No | Null | TrackStatistic_29Oct20241016UTC.xlsx

## Dashboard
Unique list of all engagements | Number of tracks | Undefined Tracks |  |  |  |  | Unique list of LCM engagements | Number of LCM engagements
2BP | 108 | PM | Engagement | Track | Status | End Date | LCM_NH | 1
OPS2
Cluster Update
Server Racking
RH Update
BS_NS-ID
Monitoring & Reporting
SBR
VM
STCK1
DS_PowerBI
STCK3
DC-0
Back-up & data replication
Cloud Migration
DevSecOps
DevOps Security
API deployment
Cloud DevOps Back-up
DS_EC
DS_CMA
DS_NO
B2C
LCM_NH
W21
iXES
XSV-NT

## Search bar
Project Manager | Engagement Name | Track Name | Phase | RAG | Handover due date | Completed
Project Manager1 | 2BP | Governance | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager1 | 2BP | Service Management | Implement | Red | 2024-11-29 | 0%
Project Manager1 | 2BP | NETWORK | Implement | Red | 2024-09-17 | 0%
Project Manager1 | 2BP | Governance v2 | Implement | Red | 2024-09-30 | 0%
Project Manager1 | OPS2 | Governance | Close | Blue | 2024-06-30 | 0%
Project Manager1 | OPS2 | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager1 | OPS2 | OPENSHIFT | Close | Blue | 2024-06-30 | 0%
Project Manager1 | Cluster Update | Governance | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | Cluster Update | SERVICE MANAGEMENT | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | Cluster Update | Platform | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | Server Racking | Governance | Close | Blue | 2024-12-27 | 0%
Project Manager1 | Server Racking | OPENSHIFT | Close | Blue | 2024-12-27 | 0%
Project Manager1 | Server Racking | Service Management | Close | Blue | 2024-12-27 | 0%
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | RH Update | ANSIBLE | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-06-27 | 0%
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-06-27 | 0%
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-06-27 | 0%
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-09-30 | 0%
Project Manager2 | BS_NS-ID | VMware | Close | Blue | 2024-04-30 | 0%
Project Manager2 | BS_NS-ID | Service Management | Implement | Red | 2024-09-30 | 0%
Project Manager2 | BS_NS-ID | Network | Close | Blue | 2023-10-31 | 0%
Project Manager2 | BS_NS-ID | Platform | Close | Blue | 2024-04-30 | 0%
Project Manager2 | BS_NS-ID | Governance | Cancelled | Undefined | 2024-04-30 | 0%
Project Manager2 | BS_NS-ID | Backup & Storage | Close | Blue | 2023-10-31 | 0%
Project Manager2 | BS_NS-ID | VDI | Close | Blue | 2023-10-31 | 0%
Project Manager2 | BS_NS-ID | Governance - v2 | Delivery | Amber | 2024-09-30 | 300%
Project Manager2 | W21 | Network | Delivery | Amber | 2024-03-31 | 600%
Project Manager2 | W21 | Security | Implement | Red | 2024-07-31 | 100%
Project Manager2 | W21 | Service Management | Implement | Red | 2024-07-31 | 800%
Project Manager2 | W21 | Governance | Implement | Red | 2024-07-31 | 300%
Project Manager3 | Monitoring & Reporting | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Back-up & data replication | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Back-up & data replication | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Back-up & data replication | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Back-up & data replication | SECURITY | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud Migration | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud Migration | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud Migration | SECURITY | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud Migration | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevSecOps | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevSecOps | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevSecOps | SECURITY | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevSecOps | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevOps Security | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevOps Security | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevOps Security | SECURITY | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | DevOps Security | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | API deployment | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | API deployment | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | API deployment | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | API deployment | Security | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud DevOps Back-up | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud DevOps Back-up | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud DevOps Back-up | Cloud | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager3 | Cloud DevOps Back-up | SECURITY | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager4 | Monitoring & Reporting | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager4 | Monitoring & Reporting | Service Management | Cancelled | Undefined | 2024-06-30 | 0%
Project Manager4 | DC-0 | BACKUP and STORAGE | Cancelled | Undefined | 2024-03-31 | 0%
Project Manager4 | DC-0 | OPENSHIFT | Cancelled | Undefined | 2024-03-31 | 0%
Project Manager4 | DC-0 | GOVERNANCE | Cancelled | Undefined | 2024-03-31 | 0%
Project Manager4 | DC-0 | Service Management | Cancelled | Undefined | 2024-03-31 | 0%
Project Manager5 | SBR | Governance | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | VMWare | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | Service Management | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | NETWORK | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | MIDDLEWARE | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | IAM Team | Implement | Red | 2024-09-19 | 0%
Project Manager5 | SBR | BACKUP & STORAGE TEAM | Implement | Red | 2024-09-19 | 0%
Project Manager5 | STCK1 | BACKUP & STORAGE TEAM | Close | Blue | 2024-05-30 | 0%
Project Manager5 | STCK1 | SERVICE MANAGEMENT | Close | Blue | 2024-05-30 | 0%
Project Manager5 | STCK1 | GOVERNANCE | Close | Blue | 2024-05-30 | 0%
Project Manager5 | STCK3 | BACKUP & STORAGE TEAM | Close | Blue | 2024-04-30 | 0%
Project Manager5 | STCK3 | Governance | Delivery | Amber | 2024-04-30 | 0%
Project Manager5 | STCK3 | SERVICE MANAGEMENT | Close | Blue | 2024-04-30 | 0%
Project Manager6 | VM | GOVERNANCE | Delivery | Green | 2024-11-30 | 0%
Project Manager6 | VM | SERVICE MANAGEMENT | Close | Blue | 2024-08-31 | 0%
Project Manager6 | VM | VMWARE | Close | Blue | 2024-06-30 | 0%
Project Manager6 | iXES | GOVERNANCE | Close | Blue | 2024-11-30 | 300%
Project Manager6 | iXES | SECURITY | Close | Blue | 2024-11-30 | 200%
Project Manager6 | iXES | SERVICE MANAGEMENT | Delivery | Amber | 2024-11-30 | 1100%
Project Manager6 | iXES | VMWARE | Close | Blue | 2024-11-30 | 600%
Project Manager6 | XSV-NT | GOVERNANCE | Delivery | Green | 2024-11-30 | 300%
Project Manager6 | XSV-NT | SERVICE MANAGEMENT | Implement | Green | 2024-11-30 | 700%
Project Manager6 | XSV-NT | SECURITY | Delivery | Green | 2024-11-30 | 200%
Project Manager6 | XSV-NT | VMWARE | Implement | Green | 2024-11-30 | 0%
Project Manager7 | DS_PowerBI | Cloud | Delivery | Amber | 2024-02-29 | 0%
Project Manager7 | DS_PowerBI | Governance | Delivery | Amber | 2024-06-30 | 0%
Project Manager7 | DS_PowerBI | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager7 | DS_EC | Cloud | Close | Blue | 2024-03-29 | 0%
Project Manager7 | DS_EC | Governance | Delivery | Amber | 2024-06-30 | 0%
Project Manager7 | DS_EC | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager7 | DS_CMA | Cloud | Close | Blue | 2024-03-29 | 0%
Project Manager7 | DS_CMA | Governance | Delivery | Amber | 2024-06-30 | 0%
Project Manager7 | DS_CMA | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager7 | DS_NO | Cloud | Close | Blue | 2024-03-29 | 0%
Project Manager7 | DS_NO | Governance | Delivery | Amber | 2024-06-30 | 0%
Project Manager7 | DS_NO | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager7 | B2C | Cloud | Close | Blue | 2024-03-29 | 0%
Project Manager7 | B2C | Governance | Delivery | Amber | 2024-06-30 | 0%
Project Manager7 | B2C | Service Management | Close | Blue | 2024-06-30 | 0%
Project Manager8 | LCM_NH | GOVERNANCE | Implement | Red | 2024-04-30 | 0%
Project Manager8 | LCM_NH | SERVICE MANAGEMENT | Configure | Red | 2024-04-30 | 0%
Project Manager8 | LCM_NH | NETWORK | Configure | Red | 2024-06-30 | 0%
Project Manager8 | DC-0 | Cloud | Cancelled | Undefined | 2024-03-31 | 0%

## SA Tracker
Project Manager | Engagement Name | Track Name | Phase | RAG | Handover due date | Days to complete | Will be breached in [days] | Handover completed | Total checks | Total Critical Checks | Completed Critical Checks | Completed | KPI_1 breached | KPI_2 breached | Source.Name | 2025-04-23
Project Manager1 | 2BP | Governance | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 19 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | Service Management | Implement | Red | 2024-11-29 | Breached |  | NULL | 14 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | NETWORK | Implement | Red | 2024-09-17 | Breached |  | NULL | 18 | 0 | 0 | 11% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | 2BP | Governance v2 | Implement | Red | 2024-09-30 | Breached |  | NULL | 8 | 3 | 0 | 25% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | Governance | Close | Blue | 2024-06-30 | Completed |  | 04-Apr-2024 | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | Service Management | Close | Blue | 2024-06-30 | Completed |  | 04-Apr-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | OPS2 | OPENSHIFT | Close | Blue | 2024-06-30 | Completed |  | 04-Apr-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | Governance | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 19 | 0 | 0 | 26% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | SERVICE MANAGEMENT | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 14 | 0 | 0 | 42% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Cluster Update | Platform | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | Governance | Close | Blue | 2024-12-27 | Completed |  | 03-Oct-2024 | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | OPENSHIFT | Close | Blue | 2024-12-27 | Completed |  | 03-Oct-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | Server Racking | Service Management | Close | Blue | 2024-12-27 | Completed |  | 03-Oct-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 19 | 0 | 0 | 21% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 14 | 0 | 0 | 14% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | ANSIBLE | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 28 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-06-27 | Cancelled |  | NULL | 19 | 0 | 0 | 31% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-06-27 | Cancelled |  | NULL | 14 | 0 | 0 | 28% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-06-27 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Governance | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 19 | 0 | 0 | 26% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Service Management | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 14 | 0 | 0 | 21% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager1 | RH Update | Platform | Cancelled | Undefined | 2024-09-30 | Cancelled |  | NULL | 17 | 0 | 0 | 11% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | VMware | Close | Blue | 2024-04-30 | Completed |  | 27-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Service Management | Implement | Red | 2024-09-30 | Breached |  | NULL | 14 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Network | Close | Blue | 2023-10-31 | Completed |  | 27-May-2024 | 18 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Platform | Close | Blue | 2024-04-30 | Completed |  | 27-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Governance | Cancelled | Undefined | 2024-04-30 | Cancelled |  | NULL | 19 | 0 | 0 | 5% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Backup & Storage | Close | Blue | 2023-10-31 | Completed |  | 27-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | VDI | Close | Blue | 2023-10-31 | Completed |  | 04-Jun-2024 | 46 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | BS_NS-ID | Governance - v2 | Delivery | Amber | 2024-09-30 | Completed |  | NULL | 8 | 3 | 3 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Monitoring & Reporting | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | Monitoring & Reporting | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 19 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | Monitoring & Reporting | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 14 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | Governance | Implement | Red | 2024-09-19 | Breached |  | NULL | 19 | 0 | 0 | 47% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | VMWare | Implement | Red | 2024-09-19 | Breached |  | NULL | 17 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | Service Management | Implement | Red | 2024-09-19 | Breached |  | NULL | 14 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | NETWORK | Implement | Red | 2024-09-19 | Breached |  | NULL | 18 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | MIDDLEWARE | Implement | Red | 2024-09-19 | Breached |  | NULL | 17 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | IAM Team | Implement | Red | 2024-09-19 | Breached |  | NULL | 17 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | SBR | BACKUP & STORAGE TEAM | Implement | Red | 2024-09-19 | Breached |  | NULL | 17 | 0 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | GOVERNANCE | Delivery | Green | 2024-11-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | SERVICE MANAGEMENT | Close | Blue | 2024-08-31 | Completed |  | 16-Sep-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | VM | VMWARE | Close | Blue | 2024-06-30 | Completed |  | 20-Jun-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | BACKUP & STORAGE TEAM | Close | Blue | 2024-05-30 | Completed |  | 30-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | SERVICE MANAGEMENT | Close | Blue | 2024-05-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK1 | GOVERNANCE | Close | Blue | 2024-05-30 | Completed |  | 30-May-2024 | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Cloud | Delivery | Amber | 2024-02-29 | Completed |  | NULL | 17 | 0 | 0 | 100% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Governance | Delivery | Amber | 2024-06-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_PowerBI | Service Management | Close | Blue | 2024-06-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | BACKUP & STORAGE TEAM | Close | Blue | 2024-04-30 | Completed |  | 06-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | Governance | Delivery | Amber | 2024-04-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager5 | STCK3 | SERVICE MANAGEMENT | Close | Blue | 2024-04-30 | Completed |  | 10-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | DC-0 | Cloud | Cancelled | Undefined | 2024-03-31 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | BACKUP and STORAGE | Cancelled | Undefined | 2024-03-31 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | OPENSHIFT | Cancelled | Undefined | 2024-03-31 | Cancelled |  | NULL | 17 | 0 | 0 | 5% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | GOVERNANCE | Cancelled | Undefined | 2024-03-31 | Cancelled |  | NULL | 19 | 0 | 0 | 21% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager4 | DC-0 | Service Management | Cancelled | Undefined | 2024-03-31 | Cancelled |  | NULL | 14 | 0 | 0 | 14% | Null | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Back-up & data replication | SECURITY | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | SECURITY | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud Migration | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 6% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | SECURITY | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevSecOps | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | SECURITY | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | DevOps Security | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | API deployment | Security | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | Service Management | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 12 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | GOVERNANCE | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 16 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | Cloud | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 17 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager3 | Cloud DevOps Back-up | SECURITY | Cancelled | Undefined | 2024-06-30 | Cancelled |  | NULL | 4 | 0 | 0 | 0% | Yes | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Cloud | Close | Blue | 2024-03-29 | Completed |  | 07-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Governance | Delivery | Amber | 2024-06-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_EC | Service Management | Close | Blue | 2024-06-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Cloud | Close | Blue | 2024-03-29 | Completed |  | 07-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Governance | Delivery | Amber | 2024-06-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_CMA | Service Management | Close | Blue | 2024-06-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Cloud | Close | Blue | 2024-03-29 | Completed |  | 07-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Governance | Delivery | Amber | 2024-06-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | DS_NO | Service Management | Close | Blue | 2024-06-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Cloud | Close | Blue | 2024-03-29 | Completed |  | 07-May-2024 | 17 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Governance | Delivery | Amber | 2024-06-30 | Completed |  | NULL | 19 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager7 | B2C | Service Management | Close | Blue | 2024-06-30 | Completed |  | 30-May-2024 | 14 | 0 | 0 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | GOVERNANCE | Implement | Red | 2024-04-30 | Breached |  | NULL | 8 | 3 | 0 | 0% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | SERVICE MANAGEMENT | Configure | Red | 2024-04-30 | Breached |  | NULL | 12 | 12 | 0 | 0% | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager8 | LCM_NH | NETWORK | Configure | Red | 2024-06-30 | Breached |  | NULL | 0 | 0 | 0 | 0% | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Network | Delivery | Amber | 2024-03-31 | Completed |  | NULL | 20 | 6 | 6 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Security | Implement | Red | 2024-07-31 | Breached |  | NULL | 4 | 2 | 1 | 75% | No | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Service Management | Implement | Red | 2024-07-31 | Breached |  | NULL | 12 | 12 | 8 | 66% | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager2 | W21 | Governance | Implement | Red | 2024-07-31 | Breached |  | NULL | 8 | 3 | 3 | 75% | Yes | Yes | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | GOVERNANCE | Close | Blue | 2024-11-30 | Completed |  | 03-Oct-2024 | 8 | 3 | 3 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | SECURITY | Close | Blue | 2024-11-30 | Completed |  | 03-Oct-2024 | 4 | 2 | 2 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | SERVICE MANAGEMENT | Delivery | Amber | 2024-11-30 | Completed |  | NULL | 12 | 12 | 11 | 91% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | iXES | VMWARE | Close | Blue | 2024-11-30 | Completed |  | 03-Oct-2024 | 19 | 6 | 6 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | GOVERNANCE | Delivery | Green | 2024-11-30 | Completed |  | NULL | 8 | 3 | 3 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | SERVICE MANAGEMENT | Implement | Green | 2024-11-30 | Breached |  | NULL | 12 | 12 | 7 | 58% | No | Null | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | SECURITY | Delivery | Green | 2024-11-30 | Completed |  | NULL | 4 | 2 | 2 | 100% | No | No | TrackStatistic_29Oct20241016UTC.xlsx
Project Manager6 | XSV-NT | VMWARE | Implement | Green | 2024-11-30 | Breached |  | NULL | 19 | 6 | 0 | 0% | No | Null | TrackStatistic_29Oct20241016UTC.xlsx
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This KPI is an indicator of whether all checklists have been added
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This KPI is an indicator of whether handover to operation completion date is breached